## Executive Summary
EPIC TO SURGIFLOW MASTER BUILD PLAN - Final Implementation Guide
Real-Time Patient Tracking • Database Integration • Longitudinal Care Monitoring
Generated: August 25, 2026 ¦ Source: SurgiFlow MasterLIVE (178 columns) + EPIC Cardiac Patient Overview (17 columns)
EXECUTIVE OVERVIEW
CURRENT STATE ANALYSIS
SurgiFlow LIVE Columns (SPL Database): | 178
Original EPIC Cardiac Report Columns: | 17
Original Analysis SurgiFlow Columns: | 41
KEY FINDING: SurgiFlow has been significantly expanded since the original analysis (178 vs 41 columns).
RECOMMENDED STRATEGY
Build a unified EPIC report that feeds directly into the SurgiFlow SharePoint List structure for seamless data ingestion.
QUICK STATISTICS
Metric | Value | Metric | Value
Total SurgiFlow Columns | 178 | Direct Match Fields | 7 (4%)
Columns from Cardiac Report | 11 | EPIC Build Required | 51 (29%)
Map/Transform Needed | 8 | Manual Entry Fields | 101 (57%)
Estimated Build Time | 5-6 weeks | Priority: HIGH fields | 25
IMMEDIATE NEXT STEPS
1. Review Column Mapping sheet - verify all 178 SurgiFlow columns are correctly mapped
2. Prioritize Build Action Items - identify which HIGH priority EPIC builds to start first
3. Add 11 Cardiac Report columns to EPIC - quick win with existing data
4. Build Surgery/VAD/Core clinical fields - essential for tracking
5. Establish EPIC→SPL data pipeline - automate the refresh process
6. Train staff on manual entry fields - ensure data quality

## Column Mapping
COMPLETE SURGIFLOW COLUMN STRUCTURE (178 Columns) - Database Schema for EPIC Integration
# | SurgiFlow Column Name | Category | EPIC Source | Action Required | Data Type | Notes
1 | Unit | Location | Department | MAP - Use Department field | Text | Maps to EPIC Department
2 | MRN | Patient ID | MRN | DIRECT MATCH | Number | Primary patient identifier - KEY FIELD
3 | Room | Location | Room | DIRECT MATCH | Text | Room and bed location
4 | Sx Date | Clinical | N/A | EPIC BUILD NEEDED | Date | Surgery date - add to EPIC report
5 | Admit Date | Clinical | Admit Date/Time | MAP - Extract date | DateTime | Parse from Admit Date/Time
6 | Surgery | Clinical | N/A | EPIC BUILD NEEDED | Text | Surgery procedure name
7 | EDD | Discharge | EDD | DIRECT MATCH | Date | Expected Discharge Date
8 | Service Line | Clinical | N/A | EPIC BUILD NEEDED | Text | Cardiac, Thoracic, etc.
9 | Has Device | Clinical | N/A | SPL MANUAL | Boolean | Device indicator
10 | Surgeon/Cardio | Provider | N/A | EPIC BUILD NEEDED | Text | Primary surgeon/cardiologist
11 | PMH/Procedures | Clinical | N/A | EPIC BUILD NEEDED | Text | Past medical history
12 | Leader Action Items | Workflow | N/A | SPL MANUAL | Text | Nurse leader tasks
13 | Clinical Needs to Continue Admission | Clinical | N/A | SPL MANUAL | Text | Ongoing needs
14 | Dispo | Discharge | Discharge Disposition | MAP - Simplify | Text | Discharge disposition
15 | Admit Reason | Clinical | N/A | EPIC BUILD NEEDED | Text | Reason for admission
16 | Age | Demographics | Age | DIRECT MATCH | Number | Patient age
17 | Chest Tube | Clinical | N/A | EPIC BUILD NEEDED | Boolean/Text | Chest tube status
18 | IV Meds | Medications | N/A | EPIC BUILD NEEDED | Text | Current IV medications
19 | AttendingMD | Provider | Attending | DIRECT MATCH | Text | Attending physician
20 | Braden | Assessment | Braden Score | DIRECT MATCH | Number | Braden skin assessment score
21 | Mentation | Clinical | N/A | SPL MANUAL | Text | Mental status (A&O, etc.)
22 | Non-Clinical DC Barriers | Discharge | N/A | SPL MANUAL | Text | Non-clinical barriers
23 | Isolation | Clinical | N/A | EPIC BUILD NEEDED | Text | Isolation precautions
24 | Rhythm | Clinical | N/A | EPIC BUILD NEEDED | Text | Cardiac rhythm
25 | Drip | Medications | N/A | EPIC BUILD NEEDED | Text | Current drips/infusions
26 | DNR | Clinical | N/A | EPIC BUILD NEEDED | Text | Code status
27 | Time Crit | Workflow | N/A | SPL MANUAL | Text | Time critical flag
28 | HD at Home or Inpatient? | Clinical | N/A | EPIC BUILD NEEDED | Text | Hemodialysis location
29 | Mobility | Clinical | N/A | SPL MANUAL | Text | Mobility status
30 | O2 Device | Clinical | N/A | EPIC BUILD NEEDED | Text | Oxygen delivery device
31 | O2L/% | Clinical | N/A | EPIC BUILD NEEDED | Text | Oxygen level/percentage
32 | DC Lounge | Discharge | N/A | SPL MANUAL | Boolean | Discharge lounge flag
33 | PO Pain | Clinical | N/A | EPIC BUILD NEEDED | Text | Oral pain management
34 | BM | Clinical | Last BM Date | ADD TO EPIC | Date | Last bowel movement - FROM CARDIAC REPORT
35 | Walk Test Completed | Clinical | N/A | SPL MANUAL | Boolean | Walk test completion
36 | Ride AVL | Discharge | N/A | SPL MANUAL | Boolean | Transportation arranged
37 | IS | Clinical | Incentive Spirometry | ADD TO EPIC | Text | IS level - FROM CARDIAC REPORT
38 | VAD Type | VAD | N/A | EPIC BUILD NEEDED | Text | Ventricular assist device type
39 | VAD Speed | VAD | N/A | EPIC BUILD NEEDED | Text | VAD speed settings
40 | Walk Test Needed | VAD | N/A | SPL MANUAL | Boolean | VAD walk test needed
41 | Dressing Changed | VAD | N/A | SPL MANUAL | Boolean | VAD dressing change status
42 | VAD Photo Uploaded | VAD | N/A | SPL MANUAL | Boolean | VAD photo documentation
43 | VAD Dressing Change Order | VAD | N/A | EPIC BUILD NEEDED | Text | VAD dressing change order
44 | VAD VS q4 AM | VAD | N/A | SPL MANUAL | Text | VAD vitals AM
45 | VAD VS q4 PM | VAD | N/A | SPL MANUAL | Text | VAD vitals PM
46 | VAD Dsr Next Due | VAD | N/A | SPL MANUAL | Date | VAD dressing next due
47 | VAD Missing Required | VAD | N/A | SPL MANUAL | Text | VAD missing requirements
48 | VAD RN | VAD | N/A | SPL MANUAL | Text | VAD nurse assigned
49 | VAD MISC NOTES | VAD | N/A | SPL MANUAL | Text | VAD miscellaneous notes
50 | VAD DND | VAD | N/A | SPL MANUAL | Text | VAD do not disturb
51 | VAD Cart | VAD | N/A | SPL MANUAL | Text | VAD cart status
52 | VAD Status | VAD | N/A | SPL MANUAL | Text | Overall VAD status
53 | Weight Verified | Clinical | Admit Weight/Last Weight | ADD TO EPIC | Boolean | Weight verification - FROM CARDIAC
54 | PH Medication? | Medications | N/A | EPIC BUILD NEEDED | Boolean | Pulmonary hypertension meds
55 | Patient Name | Patient ID | Patient Name | DIRECT MATCH | Text | Full patient name - KEY FIELD
56 | CORE Measures | Quality | N/A | EPIC BUILD NEEDED | Text | Core measures tracking
57 | Fall Risk | Assessment | Fall Risk Score | DIRECT MATCH | Number | Fall risk assessment
58 | Risk Level | Assessment | IP Risk of Unplanned Readmission | MAP | Text | Overall risk level
59 | Status | Workflow | N/A | SPL MANUAL | Text | Patient status tracking
60 | Cardiology Consult Sign-off | Consults | N/A | SPL MANUAL | Boolean | Cardio consult complete
61 | Other Diagnosis | Clinical | N/A | EPIC BUILD NEEDED | Text | Additional diagnoses
62 | EP Cardiology Consult Sign-off | Consults | N/A | SPL MANUAL | Boolean | EP consult complete
63 | EP Cardiology Consultant Name | Consults | N/A | EPIC BUILD NEEDED | Text | EP consultant name
64 | Cardiology Consultant Name | Consults | N/A | EPIC BUILD NEEDED | Text | Cardiology consultant
65 | Advanced HF Consultant Name | Consults | N/A | EPIC BUILD NEEDED | Text | Advanced HF consultant
66 | CTS Consult Sign-off | Consults | N/A | SPL MANUAL | Boolean | CTS consult complete
67 | Advanced HF Consult Sign-off | Consults | N/A | SPL MANUAL | Boolean | Advanced HF complete
68 | Pulmonary Consult Sign-off | Consults | N/A | SPL MANUAL | Boolean | Pulm consult complete
69 | CTS Consultant Name | Consults | N/A | EPIC BUILD NEEDED | Text | CTS consultant name
70 | Infectious Disease Consult Sign-off | Consults | N/A | SPL MANUAL | Boolean | ID consult complete
71 | Pulmonary Consultant Name | Consults | N/A | EPIC BUILD NEEDED | Text | Pulmonary consultant
72 | Infectious Disease Consultant Name | Consults | N/A | EPIC BUILD NEEDED | Text | ID consultant name
73 | Heme/Onco Consult Sign-off | Consults | N/A | SPL MANUAL | Boolean | Heme/Onco complete
74 | Heme/Onco Consultant Name | Consults | N/A | EPIC BUILD NEEDED | Text | Heme/Onco consultant
75 | GI Consultant Name | Consults | N/A | EPIC BUILD NEEDED | Text | GI consultant name
76 | GI Consult Sign-off | Consults | N/A | SPL MANUAL | Boolean | GI consult complete
77 | Nephrology Consultant Name | Consults | N/A | EPIC BUILD NEEDED | Text | Nephrology consultant
78 | Nephrology Consult Sign-off | Consults | N/A | SPL MANUAL | Boolean | Nephro consult complete
79 | Hospice Consult Sign-off | Consults | N/A | SPL MANUAL | Boolean | Hospice consult complete
80 | Palliative Consult Sign-off | Consults | N/A | SPL MANUAL | Boolean | Palliative complete
81 | Hospice Consultant Name | Consults | N/A | EPIC BUILD NEEDED | Text | Hospice consultant
82 | Endocrinology Consult Sign-off | Consults | N/A | SPL MANUAL | Boolean | Endo consult complete
83 | Palliative Consultant Name | Consults | N/A | EPIC BUILD NEEDED | Text | Palliative consultant
84 | Endocrinology Consultant Name | Consults | N/A | EPIC BUILD NEEDED | Text | Endo consultant name
85 | Neurology Consult Sign-off | Consults | N/A | SPL MANUAL | Boolean | Neuro consult complete
86 | Neurology Consultant Name | Consults | N/A | EPIC BUILD NEEDED | Text | Neuro consultant name
87 | Other Consultant (Misc) | Consults | N/A | SPL MANUAL | Text | Other consultant name
88 | Other Consultant (Misc) Sign-off | Consults | N/A | SPL MANUAL | Boolean | Other consult complete
89 | Active IV Meds Transition Plan | Discharge | N/A | SPL MANUAL | Text | IV to PO transition plan
90 | PT/OT Eval Completed | Discharge | N/A | EPIC BUILD NEEDED | Boolean | PT/OT evaluation done
91 | Final Destination | Discharge | Discharge Disposition | MAP | Text | Final discharge destination
92 | Disposition Misalignment Escalation | Discharge | N/A | SPL MANUAL | Text | Disposition issues
93 | Home Equipment Verified | Discharge | N/A | SPL MANUAL | Boolean | Equipment verified
94 | HHC/SNF/IPR Auth Submitted | Discharge | N/A | SPL MANUAL | Boolean | Authorization submitted
95 | DME/Supplies | Discharge | N/A | SPL MANUAL | Text | DME supplies needed
96 | DME/Supplies Other | Discharge | N/A | SPL MANUAL | Text | Other supplies
97 | Correct Pharmacy Listed | Discharge | Encounter Pharmacy | MAP | Boolean | Pharmacy verified
98 | DME/Supplies Arranged | Discharge | N/A | SPL MANUAL | Boolean | DME arranged
99 | PCP Scheduled | Follow-up | Next PCP Visit | MAP | Boolean | PCP appointment made
100 | Wound Care Instructions | Discharge | N/A | SPL MANUAL | Text | Wound care instructions
101 | Cardio Scheduled | Follow-up | Follow-up Providers | MAP | Boolean | Cardio follow-up scheduled
102 | PCP Appt Date | Follow-up | Next PCP Visit | MAP | Date | PCP appointment date
103 | CTS/Surgeon Scheduled | Follow-up | N/A | SPL MANUAL | Boolean | Surgeon follow-up
104 | Cardio Appt Date | Follow-up | N/A | EPIC BUILD NEEDED | Date | Cardiology appointment
105 | CTS/Surgeon Appt Date | Follow-up | N/A | EPIC BUILD NEEDED | Date | Surgeon appointment
106 | Bridge Services Requested | Discharge | N/A | SPL MANUAL | Boolean | Bridge services flag
107 | Bridge Services Detail | Discharge | N/A | SPL MANUAL | Text | Bridge services details
108 | Pulm Scheduled | Follow-up | N/A | SPL MANUAL | Boolean | Pulmonary follow-up
109 | Pulm Appt Date | Follow-up | N/A | EPIC BUILD NEEDED | Date | Pulmonary appointment
110 | Has A-Fib | A-Fib Protocol | N/A | EPIC BUILD NEEDED | Boolean | A-Fib diagnosis flag
111 | A-Fib Type | A-Fib Protocol | N/A | EPIC BUILD NEEDED | Text | Type of A-Fib
112 | Known: AC Restarted Inpatient | A-Fib Protocol | N/A | SPL MANUAL | Boolean | Anticoag restarted
113 | Known: AC on AVS w/ Dose | A-Fib Protocol | N/A | SPL MANUAL | Boolean | AC documented on AVS
114 | New: A-Fib Teach-back | A-Fib Protocol | N/A | SPL MANUAL | Boolean | A-Fib education done
115 | Known: AC Verified/Bridged | A-Fib Protocol | N/A | SPL MANUAL | Boolean | AC verified/bridged
116 | New: Bleeding Risk Documented | A-Fib Protocol | N/A | SPL MANUAL | Boolean | Bleeding risk noted
117 | AMI Medications | AMI Protocol | N/A | EPIC BUILD NEEDED | Text | AMI medications
118 | AMI: Heart Cath/PCI This Encounter | AMI Protocol | N/A | EPIC BUILD NEEDED | Boolean | Cath/PCI performed
119 | New: AC Prescription Provided | A-Fib Protocol | N/A | SPL MANUAL | Boolean | AC Rx provided
120 | AMI: Cardiac Rehab Referral | AMI Protocol | N/A | SPL MANUAL | Boolean | AMI cardiac rehab
121 | CABG Medications | CABG Protocol | N/A | EPIC BUILD NEEDED | Text | CABG medications
122 | CABG: This Encounter | CABG Protocol | N/A | EPIC BUILD NEEDED | Boolean | CABG this admission
123 | AMI: Provider (Date/Name) | AMI Protocol | N/A | EPIC BUILD NEEDED | Text | AMI provider info
124 | CABG: Cardiac Rehab Referral | CABG Protocol | N/A | SPL MANUAL | Boolean | CABG cardiac rehab
125 | CABG: Glycemic Control Plan | CABG Protocol | N/A | SPL MANUAL | Text | Glycemic control plan
126 | CABG: Surgeon (Date/Name) | CABG Protocol | N/A | EPIC BUILD NEEDED | Text | CABG surgeon info
127 | COPD: Inhaler/Neb Regimen Optimized | COPD Protocol | N/A | SPL MANUAL | Boolean | COPD inhaler optimized
128 | COPD: Inhaler Technique Education | COPD Protocol | N/A | SPL MANUAL | Boolean | Inhaler education done
129 | CABG: Navigator Contact AVS | CABG Protocol | N/A | SPL MANUAL | Boolean | Navigator on AVS
130 | COPD: Smoking Cessation | COPD Protocol | N/A | SPL MANUAL | Boolean | Smoking cessation addressed
131 | COPD: Steroid/Antibiotic Plan | COPD Protocol | N/A | SPL MANUAL | Text | COPD steroid/abx plan
132 | COPD: Walk Test 24-48 hrs | COPD Protocol | N/A | SPL MANUAL | Boolean | COPD walk test done
133 | COPD: Pulmonary Rehab Referral | COPD Protocol | N/A | SPL MANUAL | Boolean | COPD pulm rehab
134 | HF Medications | HF Protocol | N/A | EPIC BUILD NEEDED | Text | HF medications
135 | HF: Daily Standing Weight | HF Protocol | N/A | SPL MANUAL | Boolean | Daily weights ordered
136 | HF: Stable Weight Trend | HF Protocol | N/A | SPL MANUAL | Boolean | Weight trend stable
137 | HF: CHF Order Set EPIC | HF Protocol | N/A | EPIC BUILD NEEDED | Boolean | CHF order set used
138 | HF: Cardiac Rehab Phase I | HF Protocol | N/A | SPL MANUAL | Boolean | Phase I rehab
139 | HF: Sodium Restriction | HF Protocol | N/A | SPL MANUAL | Boolean | Na restriction
140 | HF: Sodium Restriction Value | HF Protocol | N/A | SPL MANUAL | Text | Na restriction value
141 | HF: Fluid Restriction | HF Protocol | N/A | SPL MANUAL | Boolean | Fluid restriction
142 | HF: Fluid Restriction Value | HF Protocol | N/A | SPL MANUAL | Text | Fluid restriction value
143 | HF: Diuretic Plan for DC | HF Protocol | N/A | SPL MANUAL | Boolean | Diuretic DC plan
144 | HF: Diuretic Plan Value | HF Protocol | N/A | SPL MANUAL | Text | Diuretic plan details
145 | HF: Dry Weight on AVS | HF Protocol | N/A | SPL MANUAL | Boolean | Dry weight on AVS
146 | HF: Dry Weight Value | HF Protocol | Admit Weight/Last Weight | ADD TO EPIC | Number | Dry weight value - FROM CARDIAC
147 | PNA: IS Education Teach-back | PNA Protocol | Incentive Spirometry | ADD TO EPIC | Boolean | IS education - FROM CARDIAC
148 | PNA: IS Usage Documented | PNA Protocol | Level Incentive Spirometer | ADD TO EPIC | Boolean | IS usage - FROM CARDIAC
149 | PNA: Vaccination Status Addressed | PNA Protocol | N/A | EPIC BUILD NEEDED | Boolean | Vaccination addressed
150 | Final: Escalations Completed | Final Checklist | N/A | SPL MANUAL | Boolean | Escalations complete
151 | Final: DC Med Rec by Pharmacy | Final Checklist | Dischrg Med Rec | MAP | Boolean | Med rec by pharmacy
152 | Final: IP Med Parameters on AVS | Final Checklist | N/A | SPL MANUAL | Boolean | Med parameters on AVS
153 | Final: No Duplicate Meds | Final Checklist | N/A | SPL MANUAL | Boolean | No duplicate meds
154 | Final: Reliable Transport Confirmed | Final Checklist | N/A | SPL MANUAL | Boolean | Transport confirmed
155 | Final: Zone Tool on AVS | Final Checklist | N/A | SPL MANUAL | Boolean | Zone tool on AVS
156 | Final: Core 4 Pack Given | Final Checklist | N/A | SPL MANUAL | Boolean | Core 4 pack given
157 | Final: Patient Verbalized Understanding | Final Checklist | N/A | SPL MANUAL | Boolean | Patient understanding
158 | Final: Readmission Huddle Completed Prior to DC | Final Checklist | N/A | SPL MANUAL | Boolean | Readmit huddle done
159 | Final: Nurse Leader Review | Final Checklist | N/A | SPL MANUAL | Boolean | NL review complete
160 | Final: Nurse Leader Review Date | Final Checklist | N/A | SPL MANUAL | Date | NL review date
161 | Device List | Device | N/A | EPIC BUILD NEEDED | Text | List of devices
162 | Device Presence Documented | Device | N/A | SPL MANUAL | Boolean | Device documented
163 | Devices at Discharge Identified | Device | N/A | SPL MANUAL | Boolean | DC devices identified
164 | Device Teach-back Completed | Device | N/A | SPL MANUAL | Boolean | Device education done
165 | Device DC Follow-up Addressed | Device | N/A | SPL MANUAL | Boolean | Device follow-up addressed
166 | Device Documentation Notes | Device | N/A | SPL MANUAL | Text | Device notes
167 | Med Access & Cost Resolved | Final Checklist | N/A | SPL MANUAL | Boolean | Med access resolved
168 | PNA: Steroid & Antibiotic Plan | PNA Protocol | N/A | SPL MANUAL | Text | PNA steroid/abx plan
169 | Final: New Meds & Dx Education | Final Checklist | N/A | SPL MANUAL | Boolean | New med education
170 | Final: All Meds Dose & Frequency | Final Checklist | N/A | SPL MANUAL | Boolean | All meds documented
171 | Final: AVS Reviewed w/ Patient & Family | Final Checklist | N/A | SPL MANUAL | Boolean | AVS reviewed
172 | GMLOS | Metrics | GMLOS | DIRECT MATCH | Number | Geometric mean LOS
173 | Does the patient have family/friend support for discharge? | Discharge | N/A | SPL MANUAL | Boolean | Support system
174 | POST Huddle Action Item Update | Workflow | N/A | SPL MANUAL | Text | Post huddle updates
175 | Nursing Action Item Follow Up (NM Owner) | Workflow | N/A | SPL MANUAL | Text | Nursing follow-up
176 | CM Leader Review | Workflow | N/A | SPL MANUAL | Boolean | CM review complete
177 | POST CM Huddle Follow Up | Workflow | N/A | SPL MANUAL | Text | CM huddle follow-up
178 | CSN | Patient ID | CSN | DIRECT MATCH | Number | Contact Serial Number - KEY FIELD

## Build Action Items
EPIC BUILD ACTION ITEMS - Prioritized Implementation Steps
Columns to ADD/MODIFY in EPIC Report for SurgiFlow Database Ingestion
SECTION 1: DIRECT MATCHES - Already Aligned (7 Fields)
# | SurgiFlow Field | EPIC Field | Status | Data Type | Priority | Notes | Est. Effort
1 | MRN | MRN | ✓ ALIGNED | Number | N/A | Primary patient identifier - KEY FIELD | None
2 | CSN | CSN | ✓ ALIGNED | Number | N/A | Contact Serial Number - KEY FIELD | None
3 | Patient Name | Patient Name | ✓ ALIGNED | Text | N/A | Full patient name | None
4 | Room | Room | ✓ ALIGNED | Text | N/A | Room and bed location | None
5 | Age | Age | ✓ ALIGNED | Number | N/A | Patient age | None
6 | Braden | Braden Score | ✓ ALIGNED | Number | N/A | Braden skin assessment | None
7 | Fall Risk | Fall Risk Score | ✓ ALIGNED | Number | N/A | Fall risk assessment | None
SECTION 2: ADD FROM CARDIAC REPORT - New Columns from Existing EPIC Report (11 Fields)
# | SurgiFlow Field | Cardiac Report Source | Action | Data Type | Priority | Build Instructions | Est. Effort
1 | Admit Weight | F (Admit Weight) | ADD COLUMN | Numeric + Unit | HIGH | Add IP ADT Admit Weight column from Cardiac report | Low
2 | Last Weight | G (Last Weight) | ADD COLUMN | Numeric + Unit | HIGH | Add most recent weight with conversion | Low
3 | Weight Doc/Date | H (Weight Doc/Date) | ADD COLUMN | DateTime | HIGH | Add weight documentation timestamp | Low
4 | Creatinine | I (Creatinine) | ADD COLUMN | Numeric (mg/dL) | HIGH | Add most recent creatinine lab result | Low
5 | Last K+ (Potassium) | J (Last K+) | ADD COLUMN | Numeric | HIGH | Add most recent potassium lab result | Low
6 | Magnesium | K (Magnesium) | ADD COLUMN | Numeric | HIGH | Add most recent magnesium lab result | Low
7 | Last Hgb (Hemoglobin) | L (Last Hgb) | ADD COLUMN | Numeric | HIGH | Add most recent hemoglobin lab result | Low
8 | Hester Davis Fall Score | M (Hester Davis) | ADD COLUMN | Numeric | MEDIUM | Add Hester Davis fall assessment score | Low
9 | Incentive Spirometry Freq | O (IS Frequency) | ADD COLUMN | Text | MEDIUM | Add IS ordered frequency | Low
10 | Level Incentive Spirometer | P (Level IS) | ADD COLUMN | Text + Date | MEDIUM | Add patient IS level achieved | Low
11 | Last BM Date | Q (Last BM Date) | ADD COLUMN | Date | MEDIUM | Add last bowel movement date | Low
SECTION 3: EPIC BUILD NEEDED - New Columns to Build in EPIC (45+ Fields)
# | SurgiFlow Field | Category | Action | Data Type | Priority | EPIC Build Instructions | Est. Effort
1 | Sx Date | Clinical | BUILD NEW | Date | HIGH | Add Surgery Date from surgical encounter | Medium
2 | Surgery | Clinical | BUILD NEW | Text | HIGH | Add Surgery/Procedure Name from OR data | Medium
3 | Service Line | Clinical | BUILD NEW | Text | HIGH | Add Service Line (Cardiac, Thoracic, etc.) | Low
4 | Surgeon/Cardio | Provider | BUILD NEW | Text | HIGH | Add Primary Surgeon or Cardiologist name | Medium
5 | Chest Tube | Clinical | BUILD NEW | Boolean/Text | HIGH | Add chest tube status from nursing flowsheets | Medium
6 | IV Meds | Medications | BUILD NEW | Text | HIGH | Add current IV medications list | Medium
7 | Isolation | Clinical | BUILD NEW | Text | MEDIUM | Add isolation precautions status | Low
8 | Rhythm | Clinical | BUILD NEW | Text | MEDIUM | Add cardiac rhythm from telemetry | Medium
9 | Drip | Medications | BUILD NEW | Text | MEDIUM | Add current drips/infusions | Medium
10 | DNR | Clinical | BUILD NEW | Text | MEDIUM | Add code status from patient preferences | Low
11 | HD at Home or Inpatient? | Clinical | BUILD NEW | Text | MEDIUM | Add hemodialysis location preference | Low
12 | O2 Device | Clinical | BUILD NEW | Text | MEDIUM | Add oxygen delivery device type | Low
13 | O2L/% | Clinical | BUILD NEW | Text | MEDIUM | Add oxygen level/percentage setting | Low
14 | PO Pain | Clinical | BUILD NEW | Text | MEDIUM | Add oral pain medication regimen | Medium
15 | VAD Type | VAD | BUILD NEW | Text | HIGH | Add VAD type (LVAD, RVAD, BiVAD) | Medium
16 | VAD Speed | VAD | BUILD NEW | Text | HIGH | Add VAD speed settings | Medium
17 | VAD Dressing Change Order | VAD | BUILD NEW | Text | HIGH | Add VAD dressing change order info | Medium
18 | PH Medication? | Medications | BUILD NEW | Boolean | MEDIUM | Add pulmonary hypertension med flag | Low
19 | CORE Measures | Quality | BUILD NEW | Text | HIGH | Add core measures tracking data | High
20 | Other Diagnosis | Clinical | BUILD NEW | Text | MEDIUM | Add secondary diagnoses list | Medium
21 | EP Cardiology Consultant Name | Consults | BUILD NEW | Text | MEDIUM | Add EP consultant name from consults | Medium
22 | Cardiology Consultant Name | Consults | BUILD NEW | Text | MEDIUM | Add Cardiology consultant name | Medium
23 | Advanced HF Consultant Name | Consults | BUILD NEW | Text | MEDIUM | Add Advanced HF consultant name | Medium
24 | CTS Consultant Name | Consults | BUILD NEW | Text | MEDIUM | Add CTS consultant name | Medium
25 | Pulmonary Consultant Name | Consults | BUILD NEW | Text | MEDIUM | Add Pulmonary consultant name | Medium
26 | ID Consultant Name | Consults | BUILD NEW | Text | LOW | Add Infectious Disease consultant | Medium
27 | Heme/Onco Consultant Name | Consults | BUILD NEW | Text | LOW | Add Heme/Onco consultant name | Medium
28 | GI Consultant Name | Consults | BUILD NEW | Text | LOW | Add GI consultant name | Medium
29 | Nephrology Consultant Name | Consults | BUILD NEW | Text | LOW | Add Nephrology consultant name | Medium
30 | Hospice Consultant Name | Consults | BUILD NEW | Text | LOW | Add Hospice consultant name | Medium
31 | Palliative Consultant Name | Consults | BUILD NEW | Text | LOW | Add Palliative consultant name | Medium
32 | Endo Consultant Name | Consults | BUILD NEW | Text | LOW | Add Endocrinology consultant name | Medium
33 | Neurology Consultant Name | Consults | BUILD NEW | Text | LOW | Add Neurology consultant name | Medium
34 | PT/OT Eval Completed | Discharge | BUILD NEW | Boolean | MEDIUM | Add PT/OT evaluation completion flag | Medium
35 | Cardio Appt Date | Follow-up | BUILD NEW | Date | MEDIUM | Add cardiology follow-up appointment | Medium
36 | CTS/Surgeon Appt Date | Follow-up | BUILD NEW | Date | MEDIUM | Add surgeon follow-up appointment | Medium
37 | Pulm Appt Date | Follow-up | BUILD NEW | Date | LOW | Add pulmonary follow-up appointment | Medium
38 | Has A-Fib | A-Fib Protocol | BUILD NEW | Boolean | HIGH | Add A-Fib diagnosis flag from problem list | Low
39 | A-Fib Type | A-Fib Protocol | BUILD NEW | Text | HIGH | Add A-Fib classification type | Medium
40 | AMI Medications | AMI Protocol | BUILD NEW | Text | HIGH | Add AMI medication list | Medium
41 | AMI: Heart Cath/PCI This Encounter | AMI Protocol | BUILD NEW | Boolean | HIGH | Add cath/PCI procedure flag | Medium
42 | AMI: Provider (Date/Name) | AMI Protocol | BUILD NEW | Text | MEDIUM | Add AMI provider information | Medium
43 | CABG Medications | CABG Protocol | BUILD NEW | Text | HIGH | Add CABG medication list | Medium
44 | CABG: This Encounter | CABG Protocol | BUILD NEW | Boolean | HIGH | Add CABG procedure flag this admission | Low
45 | CABG: Surgeon (Date/Name) | CABG Protocol | BUILD NEW | Text | MEDIUM | Add CABG surgeon information | Medium
46 | HF Medications | HF Protocol | BUILD NEW | Text | HIGH | Add HF medication list (GDMT) | Medium
47 | HF: CHF Order Set EPIC | HF Protocol | BUILD NEW | Boolean | MEDIUM | Add CHF order set utilization flag | Low
48 | PNA: Vaccination Status Addressed | PNA Protocol | BUILD NEW | Boolean | MEDIUM | Add vaccination status addressed flag | Low
49 | Device List | Device | BUILD NEW | Text | HIGH | Add implanted device list | High
50 | Admit Reason | Clinical | BUILD NEW | Text | HIGH | Add chief complaint/admit reason | Medium
51 | PMH/Procedures | Clinical | BUILD NEW | Text | MEDIUM | Add past medical history summary | High
SECTION 4: MAP/TRANSFORM - Existing EPIC Fields Needing Mapping (8 Fields)
# | SurgiFlow Field | EPIC Source Field | Transformation | Data Type | Priority | Mapping Logic | Est. Effort
1 | Unit | Department | MAP | Text | HIGH | Map Department value to Unit field | Low
2 | Admit Date | Admit Date/Time | EXTRACT DATE | Date | HIGH | Extract date portion from DateTime | Low
3 | Dispo | Discharge Disposition | SIMPLIFY | Text | MEDIUM | Simplify disposition to category | Low
4 | Risk Level | IP Risk of Unplanned Readmission | MAP | Text | MEDIUM | Map risk score to category | Low
5 | Final Destination | Discharge Disposition | MAP | Text | MEDIUM | Map to final destination category | Low
6 | Correct Pharmacy Listed | Encounter Pharmacy | VERIFY | Boolean | MEDIUM | Flag if pharmacy is listed | Low
7 | PCP Scheduled/Date | Next PCP Visit | EXTRACT | Boolean/Date | MEDIUM | Extract scheduled flag and date | Low
8 | Final: DC Med Rec | Dischrg Med Rec | MAP | Boolean | MEDIUM | Map med rec status to flag | Low
SECTION 5: SPL MANUAL ENTRY - No EPIC Build Required (100+ Fields)
These fields are maintained manually in SurgiFlow SharePoint List by clinical staff during huddles and rounds.
Category | Count | Examples
Workflow Fields | 15+ | Leader Action Items, Clinical Needs, Status, Time Crit, DC Lounge
Consult Sign-offs | 16 | All *Consult Sign-off fields (Boolean toggles by staff)
Protocol Checklists | 50+ | A-Fib, AMI, CABG, COPD, HF, PNA protocol checkbox fields
Final Checklist | 20+ | Final: Escalations, Med Rec, Transport, Zone Tool, Core 4, etc.
Device Tracking | 6 | Device Presence, Teach-back, DC Follow-up, Documentation Notes
VAD Manual Fields | 10+ | VAD Photo, VS q4 AM/PM, Dsr Next Due, RN, Notes, Cart, DND
Huddle Notes | 5 | POST Huddle Action Items, Nursing Follow Up, CM Review, etc.

## Changes & Deletions
CHANGES & DELETIONS - Field Modifications Required
FIELDS TO CONSOLIDATE/REMOVE FROM ORIGINAL ANALYSIS
# | Original Analysis Field | Issue | Resolution | Action | Impact | Notes
1 | Braden Score (Cardiac) | Duplicate | Already exists in SurgiFlow as Column 20 (Braden) | USE SPL FIELD | None | Verify data matches
2 | Fall Risk (Hester Davis) | Similar field exists | SurgiFlow has Fall Risk (Col 57) - compare scores | EVALUATE | TBD | May want both for comparison
3 | Blank Column (F in old analysis) | Not needed | SurgiFlow expanded - no blank columns needed | DELETE | None | Original analysis outdated
4 | Original 41-column structure | Outdated | SurgiFlow now has 178 columns | UPDATE REFERENCE | Major | Use new column mapping
FIELD NAME CHANGES - Mapping Original Analysis to Current SPL Structure
# | Original Analysis Name | Current SurgiFlow Name | Old Position | New Position | Change Type | Notes
1 | Room and Bed | Room | B | Col 3 | RENAMED | Simplified to Room only
2 | Department | Unit | A | Col 1 | RENAMED | Changed to Unit terminology
3 | EDD (Expected Discharge Date) | EDD | J | Col 7 | KEPT | Same, different position
4 | Fin Class | N/A | K | Removed | REMOVED | Not in current structure
5 | Readmission to Hospital | N/A | L | Removed | REMOVED | Not in current structure
6 | Admit Date/Time | Admit Date | M | Col 5 | SIMPLIFIED | Date only, no time
7 | Discharge Disposition | Dispo | N | Col 14 | RENAMED | Shortened name
8 | Working DRG Name | N/A | AO | Removed | REMOVED | Not in current structure
9 | Last EF (Ejection Fraction) | N/A | AK | Removed | MOVED TO HF | Part of HF Protocol section
10 | Last EF Date | N/A | AL | Removed | MOVED TO HF | Part of HF Protocol section
NEW CATEGORIES ADDED TO SURGIFLOW (Not in Original Analysis)
# | New Category | Column Count | Purpose | Data Source | Priority | Notes
1 | VAD (Ventricular Assist Device) | 15 | Complete VAD patient tracking | EPIC + Manual | HIGH | Cols 38-52
2 | Consult Sign-offs | 16 | Track consultant involvement | Manual | MEDIUM | Boolean fields
3 | Consultant Names | 14 | Identify consulting physicians | EPIC Build | MEDIUM | Text fields
4 | A-Fib Protocol | 10 | A-Fib management checklist | Mixed | HIGH | Cols 110-119
5 | AMI Protocol | 6 | AMI core measure tracking | Mixed | HIGH | Acute MI care
6 | CABG Protocol | 8 | CABG surgery checklist | Mixed | HIGH | Post-op CABG
7 | COPD Protocol | 7 | COPD management tracking | Manual | MEDIUM | Pulmonary care
8 | HF Protocol | 14 | Heart Failure GDMT tracking | Mixed | HIGH | Cols 134-146
9 | PNA Protocol | 4 | Pneumonia care tracking | Mixed | MEDIUM | PNA bundle
10 | Final Checklist | 20+ | Discharge readiness checklist | Manual | HIGH | Cols 150-171
11 | Device Tracking | 6 | Implanted device management | EPIC + Manual | HIGH | Cols 161-166
12 | Discharge Planning | 20+ | Complete DC coordination | Mixed | HIGH | Cols 89-109
13 | Follow-up Scheduling | 12 | Appointment tracking | EPIC + Manual | MEDIUM | PCP, Cardio, CTS, Pulm

## Summary Statistics
IMPLEMENTATION SUMMARY - Build Statistics & Timeline
COLUMN STATISTICS
Category | Count | % of Total | EPIC Action | Effort Level | Notes
Total SurgiFlow Columns | 178 | 100% | - | - | Complete SharePoint List schema
DIRECT MATCH (Aligned) | 7 | 4% | None required | None | MRN, CSN, Name, Room, Age, Braden, Fall Risk
ADD FROM CARDIAC | 11 | 6% | Add to report | Low | Labs, weights, IS, BM - already in EPIC
EPIC BUILD NEEDED | 51 | 29% | New columns | Med-High | Surgery, consults, protocols, devices
MAP/TRANSFORM | 8 | 4% | Transform data | Low | Date extraction, field mapping
SPL MANUAL ENTRY | 101 | 57% | None required | None | Staff entry during huddles/rounds
EFFORT BREAKDOWN
Priority | Column Count | Effort Type | Estimated Time | Dependencies | Owner
HIGH Priority | 25 | EPIC Report Build | 2-3 weeks | IS&T/Report Builder | Epic Analyst
MEDIUM Priority | 20 | EPIC Report Build | 1-2 weeks | IS&T/Report Builder | Epic Analyst
LOW Priority | 14 | Field Mapping | 1 week | None | Data Team
Add from Cardiac | 11 | Report Merge | 2-3 days | Cardiac Report access | Epic Analyst
Direct Match | 7 | Validation only | 1 day | None | Data Team
SPL Manual | 101 | No EPIC work | N/A | Staff training | Unit Leaders
RECOMMENDED IMPLEMENTATION PHASES
Phase | Duration | Focus Area | Key Actions | Deliverable | Success Criteria
Phase 1 | Week 1 | Foundation | Add 11 Cardiac Report columns to EPIC | Enhanced EPIC report | All lab/weight fields available
Phase 2 | Week 2-3 | Core Clinical | Build HIGH priority columns (Surgery, VAD, etc.) | Core clinical data | Surgery/device tracking live
Phase 3 | Week 3-4 | Consults & Follow-up | Add consultant names, appointments | Complete provider data | All consult fields populated
Phase 4 | Week 4-5 | Protocols | Build A-Fib, AMI, CABG, HF, PNA fields | Protocol compliance data | Quality metrics trackable
Phase 5 | Week 5-6 | Integration Testing | Test EPIC→SPL data flow | Validated pipeline | Automated refresh working
Phase 6 | Week 6+ | Go-Live & Optimization | Deploy, monitor, refine | Production system | Real-time tracking active
KEY BENEFITS ACHIEVED
1. Real-Time Tracking | EPIC data automatically flows to SurgiFlow for immediate visibility
2. Day-to-Day Monitoring | Daily huddle data combined with EPIC clinical data in one view
3. Longitudinal Tracking | Patient journey from admit through discharge and follow-up
4. Database Integration | SharePoint List structure enables Power BI dashboards and analytics
5. Seamless Ingestion | EPIC report format matches SPL schema for direct upload/replace/update

## Data Flow Architecture
DATA FLOW ARCHITECTURE - EPIC to SurgiFlow Integration
INTEGRATION OVERVIEW
Component | Description | Frequency | Owner
Source System | EPIC EMR - Master EPIC Report | Real-time/Scheduled | IS&T
Data Transform | Report format aligned to SPL schema | Automated | Data Team
Target System | SurgiFlow SharePoint List (178 cols) | On refresh | SPL Admin
Manual Entry | Clinical staff via SPL interface | Continuous | Unit Staff
Analytics | Power BI dashboards from SPL | Real-time | Analytics
DATA FLOW PROCESS
Step | Process | Input | Output | Timing | Error Handling
1 | EPIC Report Generation | Patient census | CSV/Excel export | Every 15 min | Retry 3x, alert
2 | Data Validation | Raw EPIC data | Validated dataset | Immediate | Log & flag errors
3 | Column Mapping | Validated data | SPL-formatted data | Immediate | Use default values
4 | MRN/CSN Matching | SPL-formatted data | Matched records | Immediate | Create new if needed
5 | SPL Update (Existing) | Matched records | Updated SPL rows | Immediate | Version control
6 | SPL Insert (New) | Unmatched records | New SPL rows | Immediate | Auto-populate defaults
7 | Manual Enrichment | Base SPL record | Complete patient record | Continuous | Required field alerts
8 | Analytics Refresh | Complete SPL data | Dashboard updates | Every 5 min | Cache if source unavailable
KEY IDENTIFIERS FOR DATA MATCHING
Identifier | Purpose | Source | SPL Column | Uniqueness | Notes
MRN | Patient identity | EPIC | Col 2 | Per patient | Primary key for patient matching
CSN | Encounter identity | EPIC | Col 178 | Per encounter | Contact Serial Number - visit level
Patient Name | Verification | EPIC | Col 55 | Not unique | Used for human verification
Admit Date | Encounter context | EPIC | Col 5 | Not unique | Helps identify specific admission
Room | Current location | EPIC | Col 3 | Not unique | Current bed assignment
TRACKING CAPABILITIES ENABLED
Tracking Type | Description | Data Sources | Update Frequency | Use Case
Real-Time Tracking | Current patient status and location | EPIC (auto) | Every 15 min | Census, acuity, bed management
Day-to-Day Tracking | Daily progress and care coordination | EPIC + Manual | Daily huddles | Discharge planning, barriers
Longitudinal Tracking | Patient journey across encounters | EPIC + SPL history | Per encounter | Readmission risk, outcomes
Quality Tracking | Protocol compliance and core measures | EPIC + Manual | Continuous | A-Fib, AMI, CABG, HF, COPD, PNA
Discharge Tracking | Transition of care milestones | EPIC + Manual | Continuous | Safe discharge readiness